## Sheet1
ID | Story | Estimation (hours) | Priority | Sprint When Finished
| Create homepage UI | 2 | 1 | 1
| Create scenario page UI | 2 | 1 | 1
| Create JSON formatting and storage | 2 | 1 | 1
| Create APIs to get and edit scenarios | 2 | 1 | 1
| Map out relationships between data entities using ER model | 4 | 1 | 1
| Support branching scenarios | 2 | 2 | 1
| Admin vs student view | 2 | 2 | 1
| Create scenario editor UI | 2 | 3 | 1
| Create class management backend | 2 | 3 | 1
| Create scenario editor backend | 2 | 3 | 1
| Create class management page UI | 3 | 3 | 1
| Docker containerization | 2 | 4 | 1
| Student grade page | 2 | 1 | 2
| Teacher grade page | 3 | 1 | 2
| Create grade page - student side | 2 | 3 | 2
| Create student-side class page | 3 | 3 | 2
| Make a class able to have multiple teachers | 1 | 3 | 2
| Create class grade page - instructor side | 3 | 5 | 2
| Add API documentation | 2 | 4 | 2
| Add ORM | 10 | 1 | 2
| Feedback generation | 2 | 1
| Setup database server and migrations | 15 | 1
| Add authentication using OAuth2.0 | 10 | 1
| Support scenario generation with AI | 5 | 2
| Store student responses to scenario for professors to review | 5 | 2
| Allow user login as student or professor | 10 | 2
| Create maintenance documentation | 10 | 2
| Move storage to UA database | 4 | 3
| WCAG 2.1 compliance | 10 | 3
| Implement non text based parts to scenarios (ex. audio) | 5 | 5
| Allow for scenarios to be marked as and graded as tests | 7 | 5